## hours
Week 5
| Estimated | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Hours in total
Ingrid | 8 | 3 |  |  | 2 | 1 |  |  | 6
Andreas | 8 | 5 | [5 empty] | 2 | 7
Jack | 8 |  |  | 3 |  |  |  |  | 3
Harry | 8 | 2 |  |  |  |  | 5 | 5 | 12
TOTAL W5 | 32 | 10 | 0 | 3 | 2 | 1 | 5 | 7 | 28
Week 6
| Estimated | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Hours in total
Ingrid | 8 | 4 |  |  |  | 3 |  | 2 | 9
Andreas | 8 | 4 | 3 |  |  | 1 | 4 | 2 | 14
Jack | 8 | [7 empty] | 0
Harry | 8 | 4 | 3 |  |  | 2 |  |  | 9
TOTAL W6 | 32 | 12 | 6 | 0 | 0 | 6 | 4 | 4 | 32
Week 7
| Estimated | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Hours in total
Ingrid | 8 | 3 |  | 1 |  |  | 1 | 2 | 7
Andreas | 8 | 5 |  |  | 3 | 2 | 3 |  | 13
Jack | 8 | [7 empty] | 0
Harry | 8 | 3 | 2 |  |  |  | 3 |  | 8
TOTAL W7 | 32 | 11 | 2 | 1 | 3 | 2 | 7 | 2 | 28
Week 8
| Estimated | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Hours in total
Ingrid | 8 | 2 |  |  | 2 |  |  | 5 | 9
Andreas | 8 | 2 |  |  | 2 |  |  | 5 | 9
Jack | 8 | [7 empty] | 0
Harry | 8 | 2 |  |  | 1 |  | 5 | 4 | 12
TOTAL W8 | 32 | 6 | 0 | 0 | 5 | 0 | 5 | 14 | 30
Week 9
| Estimated | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Hours in total
Ingrid | 8 | 3 |  | 2 |  |  | 1 |  | 6
Andreas | 8 | 6 |  |  | 4 |  | 3 |  | 13
Jack | [8 empty] | 0
Harry | 8 | 2 |  |  |  | 2 |  | 2 | 6
TOTAL W8 | 24 | 11 | 0 | 2 | 4 | 2 | 4 | 2 | 25
Week 10
| Estimated | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Hours in total
Ingrid | 8 |  | 3 |  |  | 2 |  | 3 | 8
Andreas | 8 |  | 7 |  |  |  |  | 5 | 12
Jack | [8 empty] | 0
Harry | 8 |  |  |  | 2 | 3 |  |  | 5
TOTAL W8 | 24 | 0 | 10 | 0 | 2 | 5 | 0 | 8 | 25
Week 11
| Estimated | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Hours in total
Ingrid | 10 | 3 | 3 | 3 |  |  | 1 |  | 10
Andreas | 10 | 5 | 5 |  | 3 |  |  |  | 13
Jack | [8 empty] | 0
Harry | 10 | 3 |  | 4 | 2 |  |  |  | 9
TOTAL W8 | 30 | 11 | 8 | 7 | 5 | 0 | 1 | 0 | 32
Week 12
| Estimated | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Hours in total
Ingrid | 10 | 3 | 4 |  |  | 3 |  |  | 10
Andreas | 10 | 3 | 3 |  |  | 2 |  |  | 8
Jack | [8 empty] | 0
Harry | 10 | 2 |  | 2 |  | 2 |  |  | 10
TOTAL W8 | 30 | 8 | 7 | 2 | 0 | 7 | 0 | 0 | 24

## week 5
| Total hours | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7
Expected time use | 32 | 27.4286 | 22.8571 | 18.2857 | 13.7143 | 9.1429 | 4.5714 | 0
Actual time spent | 32 | 22 | 22 | 19 | 17 | 16 | 11 | 4 | This means that we are 4 hours behind schedule, but since Jack's does not contribute we have worked 4 hours overtime

## week6
1 | Total hours | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7
Expected time use | 32 | 27.4286 | 22.8571 | 18.2857 | 13.7143 | 9.1429 | 4.5714 | 0
Actual time spent | 32 | 20 | 14 | 14 | 14 | 8 | 4 | 0 | This means that we are on schedule, but since Jack's does not contribute we have worked 8 hours overtime

## sprint1
| Total hours | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
Expected time use | 64 | 59.4286 | 54.8571 | 50.2857 | 45.7143 | 41.1429 | 36.5714 | 32 | 27.4286 | 22.8571 | 18.2857 | 13.7143 | 9.1429 | 4.5714 | 0
Actual time spent | 64 | 54 | 54 | 51 | 49 | 48 | 43 | 36 | 24 | 18 | 18 | 18 | 12 | 8 | 4
Expected hours is with Jack's hours as well. This means that we actually should not have a finished sprint.
If a sprint is finsiehd it means that other team members had to work extra to finsh all the user stories from that sprint

## week 7
1 | Total hours | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7
Expected time use | 32 | 27.4286 | 22.8571 | 18.2857 | 13.7143 | 9.1429 | 4.5714 | 0
Actual time spent | 32 | 21 | 19 | 18 | 15 | 13 | 6 | 4 | This means that we are 4 hours behind schedule, but since Jack's does not contribute we have worked 4 hours overtime

## week 8
1 | Total hours | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7
Expected time use | 32 | 27.4286 | 22.8571 | 18.2857 | 13.7143 | 9.1429 | 4.5714 | 0
Actual time spent | 32 | 26 | 26 | 26 | 21 | 21 | 16 | 2 | This means that we are 2 hours behind schedule, but since Jack's does not contribute we have worked 6 hours overtime

## sprint2
1 | Total hours | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
Expected time use | 64 | 59.4286 | 54.8571 | 50.2857 | 45.7143 | 41.1429 | 36.5714 | 32 | 27.4286 | 22.8571 | 18.2857 | 13.7143 | 9.1429 | 4.5714 | 0
Actual time spent | 64 | 53 | 51 | 50 | 47 | 45 | 38 | 36 | 30 | 30 | 30 | 25 | 25 | 20 | 6

## Release1
1 | Total hours | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14 | Day 15 | Day 16 | Day 17 | Day 18 | Day 19 | Day 20 | Day 21 | Day 22 | Day 23 | Day 24 | Day 25 | Day 26 | Day 27 | Day 28
Expected time use | 128 | 123.4286 | 118.8571 | 114.2857 | 109.7143 | 105.1429 | 100.5714 | 96 | 91.4286 | 86.8571 | 82.2857 | 77.7143 | 73.1429 | 68.5714 | 64 | 59.4286 | 54.8571 | 50.2857 | 45.7143 | 41.1429 | 36.5714 | 32 | 27.4286 | 22.8571 | 18.2857 | 13.7143 | 9.1429 | 4.5714 | 0
Actual time spent | 128 | 118 | 118 | 115 | 113 | 112 | 107 | 100 | 88 | 82 | 82 | 82 | 76 | 72 | 68 | 57 | 55 | 54 | 51 | 49 | 42 | 40 | 34 | 34 | 34 | 29 | 29 | 24 | 10
This means that we are 10 hours behind schedule, but since Jack's does not contribute we have worked a total of 22 hours overtime for this release

## week9
| Total hours | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7
Expected time use | 24 | 20.5714 | 17.1429 | 13.7143 | 10.2857 | 6.8571 | 3.4286 | 0
Actual time spent | 24 | 13 | 13 | 11 | 7 | 5 | 1 | -1

## week10
| Total hours | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7
Expected time use | 24 | 20.5714 | 17.1429 | 13.7143 | 10.2857 | 6.8571 | 3.4286 | 0
Actual time spent | 24 | 24 | 14 | 14 | 12 | 7 | 7 | -1

## sprint3
| Total hours | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
Expected time use | 48 | 44.5714 | 41.1429 | 37.7143 | 34.2857 | 30.8571 | 27.4286 | 24 | 20.5714 | 17.1429 | 13.7143 | 10.2857 | 6.8571 | 3.4286 | 0
Actual time spent | 48 | 37 | 37 | 35 | 31 | 29 | 25 | 23 | 23 | 13 | 13 | 11 | 6 | 6 | -2
The estimates this spirint are more accurate compared to the sprints in the first release, as we decided to remove Jacks hours. We used 2 more hours than estimated, that isn't too bad as we knew we had some catching up to do.

## week 11
| Total hours | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7
Expected time use | 30 | 25.7143 | 21.4286 | 17.1429 | 12.8571 | 8.5714 | 4.2857 | 0
Actual time spent | 30 | 19 | 11 | 4 | -1 | -1 | -2 | -2

## week 12
| Total hours | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7
Expected time use | 30 | 25.7143 | 21.4286 | 17.1429 | 12.8571 | 8.5714 | 4.2857 | 0
Actual time spent | 30 | 22 | 15 | 13 | 13 | 6 | 6 | 6

## sprint4
| Total hours | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
Expected time use | 60 | 55.7143 | 51.4286 | 47.1429 | 42.8571 | 38.5714 | 34.2857 | 30 | 25.7143 | 21.4286 | 17.1429 | 12.8571 | 8.5714 | 4.2857 | 0
Actual time spent | 60 | 49 | 41 | 34 | 29 | 29 | 28 | 28 | 20 | 13 | 11 | 11 | 4 | 4 | 4
We used a lot of time early on in the sprint, as all of the team members didn't have time at the end of the sprint. We used 4 less than estimated, which is primarily beacuse we had used a lot of time in the previous sprint to finish all user stories.

## release 2
| Total hours | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14 | Day 15 | Day 16 | Day 17 | Day 18 | Day 19 | Day 20 | Day 21 | Day 22 | Day 23 | Day 24 | Day 25 | Day 26 | Day 27 | Day 28
Expected time use | 108 | 104.1429 | 100.2857 | 96.4286 | 92.5714 | 88.7143 | 84.8571 | 81 | 77.1429 | 73.2857 | 69.4286 | 65.5714 | 61.7143 | 57.8571 | 54 | 50.1429 | 46.2857 | 42.4286 | 38.5714 | 34.7143 | 30.8571 | 27 | 23.1429 | 19.2857 | 15.4286 | 11.5714 | 7.7143 | 3.8571 | 0
Actual time spent | 108 | 97 | 97 | 95 | 91 | 89 | 85 | 83 | 83 | 73 | 73 | 71 | 66 | 66 | 58 | 47 | 39 | 32 | 27 | 27 | 26 | 26 | 18 | 11 | 9 | 9 | 2 | 2 | 2
The workflow in the team has been pretty much as expected, which is nicely illustraded in the burndown chart of the release. We have had some periods where we've had to catch up, but in the end we used 2 hours less than estimated.