## hours
Week 5
| Estimated | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Hours in total
Ingrid | 8 | 3 |  |  | 2 | 1 |  |  | 6
Andreas | 8 | 5 | [5 empty] | 2 | 7
Jack | 8 |  |  | 3 |  |  |  |  | 3
Harry | 8 | 2 |  |  |  |  | 5 | 5 | 12
TOTAL W5 | 32 | 10 | 0 | 3 | 2 | 1 | 5 | 7 | 28
Week 6
| Estimated | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Hours in total
Ingrid | 8 | 4 |  |  |  | 3 |  | 2 | 9
Andreas | 8 | 4 | 3 |  |  | 1 | 4 | 2 | 14
Jack | 8 | [7 empty] | 0
Harry | 8 | 4 | 3 |  |  | 2 |  |  | 9
TOTAL W6 | 32 | 12 | 6 | 0 | 0 | 6 | 4 | 4 | 32
Week 7
| Estimated | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Hours in total
Ingrid | 8 | 3 |  | 1 |  |  | 1 | 2 | 7
Andreas | 8 | 5 |  |  | 3 | 2 | 3 |  | 13
Jack | 8 | [7 empty] | 0
Harry | 8 | 3 | 2 |  |  |  | 3 |  | 8
TOTAL W7 | 32 | 11 | 2 | 1 | 3 | 2 | 7 | 2 | 28
Week 8
| Estimated | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Hours in total
Ingrid | 8 | 2 |  |  | 2 |  |  | 5 | 9
Andreas | 8 | 2 |  |  | 2 |  |  | 5 | 9
Jack | 8 | [7 empty] | 0
Harry | 8 | 2 |  |  | 1 |  | 5 | 4 | 12
TOTAL W8 | 32 | 6 | 0 | 0 | 5 | 0 | 5 | 14 | 30
Week 9
| Estimated | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Hours in total
Ingrid | 8 | 3 |  | 2 |  |  | 1 |  | 6
Andreas | 8 | 6 |  |  | 4 |  | 3 |  | 13
Jack | [8 empty] | 0
Harry | 8 | 2 |  |  |  | 2 |  | 2 | 6
TOTAL W8 | 24 | 11 | 0 | 2 | 4 | 2 | 4 | 2 | 25
Week 10
| Estimated | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Hours in total
Ingrid | 8 |  | 3 |  |  | 2 |  | 3 | 8
Andreas | 8 |  | 7 |  |  |  |  | 5 | 12
Jack | [8 empty] | 0
Harry | 8 |  |  |  | 2 | 3 |  |  | 5
TOTAL W8 | 24 | 0 | 10 | 0 | 2 | 5 | 0 | 8 | 25

## week 5
1 | Total hours | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7
Expected time use | 32 | 27.4286 | 22.8571 | 18.2857 | 13.7143 | 9.1429 | 4.5714 | 0
Actual time spent | 32 | 22 | 22 | 19 | 17 | 16 | 11 | 4 | This means that we are 4 hours behind schedule, but since Jack's does not contribute we have worked 4 hours overtime

## week6
1 | Total hours | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7
Expected time use | 32 | 27.4286 | 22.8571 | 18.2857 | 13.7143 | 9.1429 | 4.5714 | 0
Actual time spent | 32 | 20 | 14 | 14 | 14 | 8 | 4 | 0 | This means that we are on schedule, but since Jack's does not contribute we have worked 8 hours overtime

## sprint1
1 | Total hours | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
Expected time use | 64 | 59.4286 | 54.8571 | 50.2857 | 45.7143 | 41.1429 | 36.5714 | 32 | 27.4286 | 22.8571 | 18.2857 | 13.7143 | 9.1429 | 4.5714 | 0
Actual time spent | 64 | 54 | 54 | 51 | 49 | 48 | 43 | 36 | 24 | 18 | 18 | 18 | 12 | 8 | 4
Expected hours is with Jack's hours as well. This means that we actually should not have a finished sprint.
If a sprint is finsiehd it means that other team members had to work extra to finsh all the user stories from that sprint

## week 7
1 | Total hours | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7
Expected time use | 32 | 27.4286 | 22.8571 | 18.2857 | 13.7143 | 9.1429 | 4.5714 | 0
Actual time spent | 32 | 21 | 19 | 18 | 15 | 13 | 6 | 4 | This means that we are 4 hours behind schedule, but since Jack's does not contribute we have worked 4 hours overtime

## week 8
1 | Total hours | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7
Expected time use | 32 | 27.4286 | 22.8571 | 18.2857 | 13.7143 | 9.1429 | 4.5714 | 0
Actual time spent | 32 | 26 | 26 | 26 | 21 | 21 | 16 | 2 | This means that we are 2 hours behind schedule, but since Jack's does not contribute we have worked 6 hours overtime

## sprint2
1 | Total hours | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
Expected time use | 64 | 59.4286 | 54.8571 | 50.2857 | 45.7143 | 41.1429 | 36.5714 | 32 | 27.4286 | 22.8571 | 18.2857 | 13.7143 | 9.1429 | 4.5714 | 0
Actual time spent | 64 | 53 | 51 | 50 | 47 | 45 | 38 | 36 | 30 | 30 | 30 | 25 | 25 | 20 | 6

## Release1
1 | Total hours | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14 | Day 15 | Day 16 | Day 17 | Day 18 | Day 19 | Day 20 | Day 21 | Day 22 | Day 23 | Day 24 | Day 25 | Day 26 | Day 27 | Day 28
Expected time use | 128 | 123.4286 | 118.8571 | 114.2857 | 109.7143 | 105.1429 | 100.5714 | 96 | 91.4286 | 86.8571 | 82.2857 | 77.7143 | 73.1429 | 68.5714 | 64 | 59.4286 | 54.8571 | 50.2857 | 45.7143 | 41.1429 | 36.5714 | 32 | 27.4286 | 22.8571 | 18.2857 | 13.7143 | 9.1429 | 4.5714 | 0
Actual time spent | 128 | 118 | 118 | 115 | 113 | 112 | 107 | 100 | 88 | 82 | 82 | 82 | 76 | 72 | 68 | 57 | 55 | 54 | 51 | 49 | 42 | 40 | 34 | 34 | 34 | 29 | 29 | 24 | 10
This means that we are 10 hours behind schedule, but since Jack's does not contribute we have worked a total of 22 hours overtime for this release

## week9
| Total hours | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7
Expected time use | 24 | 20.5714 | 17.1429 | 13.7143 | 10.2857 | 6.8571 | 3.4286 | 0
Actual time spent | 24 | 13 | 13 | 11 | 7 | 5 | 1 | -1

## week10
| Total hours | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7
Expected time use | 24 | 20.5714 | 17.1429 | 13.7143 | 10.2857 | 6.8571 | 3.4286 | 0
Actual time spent | 24 | 24 | 14 | 14 | 12 | 7 | 7 | -1

## sprint3
| Total hours | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
Expected time use | 48 | 44.5714 | 41.1429 | 37.7143 | 34.2857 | 30.8571 | 27.4286 | 24 | 20.5714 | 17.1429 | 13.7143 | 10.2857 | 6.8571 | 3.4286 | 0
Actual time spent | 48 | 37 | 37 | 35 | 31 | 29 | 25 | 23 | 23 | 13 | 13 | 11 | 6 | 6 | -2