## hours
Week 5
| Estimated | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Hours in total
Ingrid | 8 | 3 |  |  | 2 | 1 |  |  | 6
Andreas | 8 | 5 | [5 empty] | 2 | 7
Jack | 8 |  |  | 3 |  |  |  |  | 3
Harry | 8 | 2 |  |  |  |  | 5 | 5 | 12
TOTAL W5 | 32 | 10 | 0 | 3 | 2 | 1 | 5 | 7 | 28
Week 6
| Estimated | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Hours in total
Ingrid | 8 | 4 |  |  |  | 3 |  | 2 | 9
Andreas | 8 | 4 | 3 |  |  | 1 | 4 | 2 | 14
Jack | 8 | [7 empty] | 0
Harry | 8 | 4 | 3 |  |  | 2 |  |  | 9
TOTAL W6 | 32 | 12 | 6 | 0 | 0 | 6 | 4 | 4 | 32
Week 7
| Estimated | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Hours in total
Ingrid | 8 | 3 |  | 1 |  |  | 1 | 2 | 7
Andreas | 8 | 5 |  |  | 3 | 2 | 3 |  | 13
Jack | 8 | [7 empty] | 0
Harry | 8 | 3 | 2 |  |  |  | 3 |  | 8
TOTAL W7 | 32 | 11 | 2 | 1 | 3 | 2 | 7 | 2 | 28
Week 8
| Estimated | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Hours in total
Ingrid | 8 | 2 |  |  | 2 |  |  | 5 | 9
Andreas | 8 | 2 |  |  | 2 |  |  | 5 | 9
Jack | 8 | [7 empty] | 0
Harry | 8 | 2 |  |  | 1 |  | 5 | 4 | 12
TOTAL W8 | 32 | 6 | 0 | 0 | 5 | 0 | 5 | 14 | 30

## week 5
1 | Total hours | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7
Expected time use | 32.00 | 27.43 | 22.86 | 18.29 | 13.71 | 9.14 | 4.57 | 0.00
Actual time spent | 32.00 | 22.00 | 22.00 | 19.00 | 17.00 | 16.00 | 11.00 | 4.00 | This means that we are 4 hours behind schedule, but since Jack's does not contribute we have worked 4 hours overtime

## week6
1 | Total hours | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7
Expected time use | 32.00 | 27.43 | 22.86 | 18.29 | 13.71 | 9.14 | 4.57 | 0.00
Actual time spent | 32.00 | 20.00 | 14.00 | 14.00 | 14.00 | 8.00 | 4.00 | 0.00 | This means that we are on schedule, but since Jack's does not contribute we have worked 8 hours overtime

## sprint1
1 | Total hours | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
Expected time use | 64.00 | 59.43 | 54.86 | 50.29 | 45.71 | 41.14 | 36.57 | 32.00 | 27.43 | 22.86 | 18.29 | 13.71 | 9.14 | 4.57 | 0.00
Actual time spent | 64.00 | 54.00 | 54.00 | 51.00 | 49.00 | 48.00 | 43.00 | 36.00 | 24.00 | 18.00 | 18.00 | 18.00 | 12.00 | 8.00 | 4.00
Expected hours is with Jack's hours as well. This means that we actually should not have a finished sprint.
If a sprint is finsiehd it means that other team members had to work extra to finsh all the user stories from that sprint

## week 7
1 | Total hours | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7
Expected time use | 32.00 | 27.43 | 22.86 | 18.29 | 13.71 | 9.14 | 4.57 | 0.00
Actual time spent | 32.00 | 21.00 | 19.00 | 18.00 | 15.00 | 13.00 | 6.00 | 4.00 | This means that we are 4 hours behind schedule, but since Jack's does not contribute we have worked 4 hours overtime

## week 8
1 | Total hours | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7
Expected time use | 32.00 | 27.43 | 22.86 | 18.29 | 13.71 | 9.14 | 4.57 | 0.00
Actual time spent | 32.00 | 26.00 | 26.00 | 26.00 | 21.00 | 21.00 | 16.00 | 2.00 | This means that we are 2 hours behind schedule, but since Jack's does not contribute we have worked 6 hours overtime

## sprint2
1 | Total hours | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
Expected time use | 64.00 | 59.43 | 54.86 | 50.29 | 45.71 | 41.14 | 36.57 | 32.00 | 27.43 | 22.86 | 18.29 | 13.71 | 9.14 | 4.57 | 0.00
Actual time spent | 64.00 | 53.00 | 51.00 | 50.00 | 47.00 | 45.00 | 38.00 | 36.00 | 30.00 | 30.00 | 30.00 | 25.00 | 25.00 | 20.00 | 6.00

## Release1
1 | Total hours | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14 | Day 15 | Day 16 | Day 17 | Day 18 | Day 19 | Day 20 | Day 21 | Day 22 | Day 23 | Day 24 | Day 25 | Day 26 | Day 27 | Day 28
Expected time use | 128.00 | 123.43 | 118.86 | 114.29 | 109.71 | 105.14 | 100.57 | 96.00 | 91.43 | 86.86 | 82.29 | 77.71 | 73.14 | 68.57 | 64.00 | 59.43 | 54.86 | 50.29 | 45.71 | 41.14 | 36.57 | 32.00 | 27.43 | 22.86 | 18.29 | 13.71 | 9.14 | 4.57 | 0.00
Actual time spent | 128.00 | 118.00 | 118.00 | 115.00 | 113.00 | 112.00 | 107.00 | 100.00 | 88.00 | 82.00 | 82.00 | 82.00 | 76.00 | 72.00 | 68.00 | 57.00 | 55.00 | 54.00 | 51.00 | 49.00 | 42.00 | 40.00 | 34.00 | 34.00 | 34.00 | 29.00 | 29.00 | 24.00 | 10.00
This means that we are 10 hours behind schedule, but since Jack's does not contribute we have worked a total of 22 hours overtime for this release